## Slide 1: COLLABORATIVE PLANNING ROADMAP
P6: Clause 32 High Level Planning
CL32 updated weekly using 4 week magnet board programme and through information gathered in Thursday Collab part 1 meeting. CL 32 submitted monthly to NH on WD -7. Programme Feeds directly into 12 wk. Look Ahead.
Satisfaction Measure: Key milestone & activities identified with dates.
12 Wk. Look
Ahead
Daily Huddle (Start of Shift)
Production Planning
Daily Huddle
(End of Shift)
Review shift performance.
Next shift Task Make Ready discussion.
Satisfaction Measure: 100% TMR. Safety, quality & production targets met.
Frequency: Daily (End of Shift).
Weekly Lockdown
Meeting
Continuous
Improvement
Weekly Lockdown meeting with Senior Management Team where agreed programme is ‘locked in’ for the next week.
Update also provides a route of escalation and transparency over programme performance and issues/blockers identified in previous week.
P6 & Short Term Planning Tool updated.
Satisfaction Measure: 100% TMR & 100% PPC.
Frequency: Weekly
12 week look ahead planning session to agree schedule of activities to be undertaken and key stakeholders.
Satisfaction Measure: Detailed 12 week plan.
Frequency: 12 weekly.
Review Performance metrics including Productivity, TMR, Lessons Learnt and Successes.
Make necessary process adjustments to remove waste and create flow.
Frequency: Monthly
Task Make Ready
Review the 12 week look ahead plan with all stakeholders.
Satisfaction Measure: 100% All blockers to flow have been identified and countermeasures agreed and allocated. (8 Blockers to Flow)
Frequency: As Required.
Review 12 week look ahead for task make ready activities.
Confirm two week look ahead, inc clash detection.
Review previous week activity.
Satisfaction Measure: 100% TMR & 100% PPC (Weekly).
Frequency: Weekly.
Daily briefing (i.e safety, quality).Review previous shift performance (did we do what we said we were going to do). Confirm shift ahead activities.‘Task Make Ready’ (8 Blockers to Flow).
Agree planned outputs
Satisfaction Measure: Performance Metric reviews inc safety, quality, productivity and Task Make Ready.
Frequency: Daily (Start of Shift).