## VPMAv2.2
| Overall Lean Visual Performance Management Score Level | 0 | National Highways Visual Performance Management Assessment v2.2
| Scheme/Team: | [5 empty] | No Evidence
| Assessment by: | [5 empty] | Little
| Date: | [5 empty] | Some
The purpose of this visual performance management assessment is to identify current good practice and areas for improvement in visual performance management on a scheme. It is an assessment of all visual performance management for the scheme, not limited to collaborative planning only. Schemes should aim to achieve a minimum of level 3 in each area. | [6 empty] | Most
All
Area | Format and content We are displaying the right content to allow whole scheme performance to be understood at a glance. It is up to date and we are using it to drive our decision making. | Select | Evidence / Comments | Section Score | 0
1.1 | Visual Management Boards are in place and accessible to anyone on site or virtually |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
1.2 | Scheme KPI's & Productivity measures are up to date with targets, actual performance and trends shown |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
1.3 | Visual information is shown for People, Continuous Improvement activity and Performance, including Safety, Customer and Delivery. |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
1.4 | 3C's in place and up to date with effective mitigation measures, owners and review dates |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
1.5 | Risks, constraints and dependencies are visible with evidence of mitigation / management |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
Area | Process Our performance meetings are attended by the right people, follow a standard process and are not reliant on a single person. The actions from the meeting result in improved scheme performance. | Select | Evidence / Comments | Section Score | 0
2.1 | Performance Meeting attendance appropriate and punctual (with dial in options available) |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
2.2 | Meetings held daily/weekly appropriate to stage |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
2.3 | Meeting follows flow of board / agenda consistently |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
2.4 | Actions taken ('just do its') are visible, owned and dated for review |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
2.5 | Progress on actions/3Cs is monitored, measured and escalated if appropriate |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
Area | People: Actions The meeting is focussed and the data used effectively to identify actions required The meetings add value for participants. | Select | Evidence / Comments | Section Score | 0
3.1 | Participants focus on exceptions (above or below target, new information) |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
3.2 | All attendees participate actively and effectively |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
3.3 | Attendance adds value and is reviewed regularly |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
3.4 | Data is being used to drive activity (Lean projects, 3Cs, Celebrating Success) |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
3.5 | Escalation requirements identified and managed |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
Area | People: Leadership The meeting is led effectively and behaviours are appropriately managed. Senior leaders visibly support the process and escalations are well managed. | Select | Evidence / Comments | Section Score | 0
4.1 | Meeting leadership is positive and focussed |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
4.2 | Meeting lead has prepared and ensured others have prepared/updated prior to start |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
4.3 | Behaviours are challenged appropriately |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
4.4 | Leadership team representatives regularly and frequently attend |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
4.5 | Leadership visibly/vocally support the process and provide escalation feedback |  |  |  |  | FALSE | FALSE | FALSE | FALSE | FALSE
Level Classification and Expectations |  | Typical Activities and Behaviours
Level 4 - Excellent continous improvement culture adopted for whole scheme deilvering significant benefits with all team members/suppliers/ stakeholders engaged |  | All teams adopt all aspects of the visual management and use this as a primary tool for project information and performance. The teams proactively undertake continuous improvement activities. Evidence of an improved system being developed as the scheme progesses.
Level 3 - Good practice and delivering performance improvement in all key and most other areas |  | All senior and most other team members support visual management and undertake continuous improvement activities, good practice is shared within the wider highways community. Benefits are tracked and high performance levels are evident in key areas.
Level 2 - Developing and delivering in specific areas |  | Visual management is widely adopted by most teams, continuous improvement visible in specfic areas and is performance is routinely tracked to indentify areas for action. Benefits are being realised.
Level 1 - Initial fragmented activity |  | There is some visual management undertaken with some key work teams committed, but there is limited engagement with the wider team.
Level 0 - Process not started and no systems in place |  | There is little evidence of the processes taking place and where implemented activity is sporadic, benefits are not recorded and lacks focus.